## QC Checklist
Construction Quality Control Checklist
Hold points for a residential build. Sign each one before the next trade covers it.
Project: |  |  | Superintendent:
Address: |  |  | Date started:
Phase | Hold point — check before covering | Status | Checked by | Date | Photo? | Notes / deficiency
Site & foundation | Excavation depth and bearing confirmed against drawings
Site & foundation | Footing dimensions, rebar size and cover verified before pour
Site & foundation | Foundation damp-proofing and drainage tile complete
Site & foundation | Backfill free of debris; grade falls away from building
Framing | Wall layout matches drawings; openings correct size and position
Framing | Headers, beams and point loads sized and bearing correctly
Framing | Sheathing nailing pattern per spec; no overdriven fasteners
Framing | Roof trusses braced and tied down per engineer's detail
Envelope | Window and door flashing lapped correctly, shingle-style
Envelope | Weather-resistive barrier continuous; penetrations sealed
Envelope | Roof underlayment, ice and water shield at eaves and valleys
Rough-in | Plumbing rough-in pressure tested and inspected
Rough-in | Electrical rough-in inspected; boxes flush and secured
Rough-in | HVAC ducts sealed, supported and pressure tested
Rough-in | Fire blocking and draft stopping complete
Insulation | Insulation full-depth, no compression or gaps at corners
Insulation | Vapour barrier continuous; penetrations sealed and taped
Insulation | Blower door / air tightness test if required by code
Interior | Drywall fastening pattern correct; no blown corners
Interior | Tile substrate and waterproofing verified before tiling
Interior | Cabinet and millwork scribes, reveals and hardware operation
Interior | Paint coverage checked under raking light
Mechanical | Fixtures operate; no leaks after 24 hours
Mechanical | HVAC balanced; registers deliver design airflow
Mechanical | Panel labelled; GFCI/AFCI devices tested
Handover | Deficiency list walked with client and dated
Handover | Warranties, manuals and as-builts handed over
Handover | Final clean complete; site photographs recorded
Not legal or code advice. Hold points and inspection requirements are set by your local authority having jurisdiction and your contract — confirm both.