## Look-ahead schedule
CONSTRUCTION SCHEDULE
Enter a start date and a duration. Finish dates, float and slipped tasks work themselves out.
Project
Data date (today)
# | Task | Trade / crew | Start | Working days | Finish | % complete | Status | Predecessor | Notes
1 | Site prep & demolition | Own crew |  | 5 |  | 0%
2 | Excavation | Excavation sub |  | 3 |  | 0% |  | 1
3 | Footings & foundation | Concrete sub |  | 8 |  | 0% |  | 2
4 | Backfill & rough grade | Excavation sub |  | 2 |  | 0% |  | 3
5 | Framing | Own crew |  | 12 |  | 0% |  | 4
6 | Roofing | Roofing sub |  | 5 |  | 0% |  | 5
7 | Windows & exterior doors | Own crew |  | 3 |  | 0% |  | 6
8 | Mechanical rough-in | HVAC sub |  | 5 |  | 0% |  | 7
9 | Plumbing rough-in | Plumbing sub |  | 5 |  | 0% |  | 8
10 | Electrical rough-in | Electrical sub |  | 5 |  | 0% |  | 9
11 | Insulation & vapour barrier | Insulation sub |  | 3 |  | 0% |  | 10
12 | Drywall, tape & sand | Drywall sub |  | 10 |  | 0% |  | 11
13 | Interior finishing | Own crew |  | 12 |  | 0% |  | 12
14 | Flooring | Flooring sub |  | 5 |  | 0% |  | 13
15 | Painting | Painting sub |  | 6 |  | 0% |  | 14
16 | Final mechanical & electrical | Subs |  | 4 |  | 0% |  | 15
17 | Deficiencies & handover | Own crew |  | 5 |  | 0% |  | 16
Project start
Project finish
Working days
Tasks late
Enter a start date in D8 and every following task chains from the one above it using WORKDAY, which skips weekends. Break the chain on any row by typing a date over the formula — useful when a trade can start before the previous one finishes. Statutory holidays are not excluded; add a holidays range to the WORKDAY calls if you need them.
Template by BuildersBridge (buildersbridge.ca) — free to use and edit.
Formulas:
Finish = IF(OR([Start]="",[Working days]=""),"",WORKDAY([Start],[Working days]-1))
Start = IF([Finish, row above]="","",WORKDAY([Finish, row above],1))
Start = IF(OR(D26="",[Start, row above]=""),"",NETWORKDAYS(D26,[Start, row above]))