## Preconstruction Agreement
Preconstruction Agreement — Scope & Terms Checklist
What the agreement should define before preconstruction work begins. This is a checklist, NOT a contract. Have a lawyer in your jurisdiction draft or review the agreement itself.
Project: Client: Date:
# | Section | What the agreement must define | Covered? | Who confirms | Notes
1 | Parties & project | Legal names of both parties, project address, and the legal description of the site
2 | Parties & project | Who at each party has authority to approve scope and fee changes
3 | Scope of services | The preconstruction services included, listed individually rather than as a category
4 | Scope of services | Services expressly excluded, so their later addition is a priced change
5 | Scope of services | Number of design or estimate revisions included before additional fees apply
6 | Deliverables | Each deliverable named, with its format and level of detail (concept estimate, detailed estimate, schedule, constructability review)
7 | Deliverables | The accuracy range each estimate is represented to carry, and what it is based on
8 | Fee & payment | The preconstruction fee, and whether it is fixed, hourly, or a percentage
9 | Fee & payment | Invoicing frequency and payment terms in days
10 | Fee & payment | Whether the preconstruction fee is credited against the construction contract if the project proceeds
11 | Fee & payment | Reimbursable expenses: what qualifies, and whether a markup applies
12 | Fee & payment | Applicable tax treatment for the jurisdiction the work is performed in
13 | Schedule | Start date, and the duration or completion date for the preconstruction phase
14 | Schedule | Client response times the schedule assumes, and what happens when they slip
15 | Assumptions | Allowances carried, and the basis for each one
16 | Assumptions | Assumptions the estimate relies on, stated so they can be tested rather than discovered later
17 | Site information | Who supplies survey, geotechnical, environmental and existing-conditions information
18 | Site information | Site access arrangements for investigation, and who bears the cost of restoration
19 | Design | Who holds design responsibility, and the design status the estimate is priced against
20 | Design | How drawing revisions during preconstruction affect the fee and the schedule
21 | Permits | Who is responsible for applications, fees, and responding to authority comments
22 | Conversion | Whether the parties intend to proceed to a construction contract, and on what basis
23 | Conversion | The contract form intended for construction, and any pricing basis carried forward
24 | Conversion | What happens to the work product if the project does not proceed
25 | Documents | Ownership of, and licence to use, estimates, drawings and models produced
26 | Documents | Confidentiality obligations, and their duration
27 | Insurance | Insurance each party carries during preconstruction, with limits
28 | Termination | Termination rights for each party, notice period, and what is payable on termination
29 | Dispute resolution | The dispute process and the governing jurisdiction
30 | Lien & payment legislation | Whether provincial or state construction payment and lien legislation applies to preconstruction services in your jurisdiction
This checklist identifies terms a preconstruction agreement commonly addresses. It is general information, not legal advice, and it is not a contract. Requirements differ by province, state and project. Have the agreement drafted or reviewed by a lawyer qualified in your jurisdiction before either party signs.